## Sheet1
POAM # | Item and/or Weakness | Responsible user or Office | Estimated Resource Cost | Scheduled Completion | Concerned Milestones | Changes to Milestones | Issue Identified in Control Documentation?
POAM 1 | AC-2 [SECTION h.] | Database Administrators | ~1-3 Work Days | Post-Implementation | Control AC-2 | Implement a notification system and document notifcation policy | "Notification" is documented to be done manually, by recurring checks on the affected items.
POAM 2 | AC-7 | Database Administrators | ~1-3 Hours | Post-Implementation | Control AC-7 | setting the right login attempt and locking time regarding the company policy | login attempt and locking time should be regarding the company policy instead of setting an amount randomly
POAM 3 | AC-8 | Database Administrators | ~3-7 Work Days | Post-Implementation | Control AC-8 | Implementing a system-use notification system after login of database | Login notifications are not in the MySQL Platform and could not be implemented exactly as the control description. Could be implemented if MySQL was paired with another platform or service.
POAM 4 | AT-4 [SECTION b.] | Database Manager | ~1 Work Day | Post-Implementation | Control AT-4 | Define and implement the policy for the time required to retain the individual records of training. | The policy is not defined and documentation with records is retained or removed improperly.