## Sheet1
POAM # | Item and/or Weakness | Responsible user or Office | Estimated Resource Cost | Scheduled Completion | Concerned Milestones | Changes to Milestones | Issue Identified in Control Documentation?
POAM 1 | AC-2 [SECTION h.] | Database Administrators | ~1-3 Work Days | Post-Implementation | Control AC-2 | Implement a notification system and document notifcation policy | "Notification" is documented to be done manually, by recurring checks on the affected items.
POAM 2 | AC-7 | Database Administrators | ~1-3 Hours | Post-Implementation |  | setting the right login attempt and locking time regarding the company policy | login attempt and locking time should be regarding the company policy instead of setting an amount randomly
POAM 3 | AC-8 | Database Administrators | ~3-7 Work Days | Post-Implementation | Control AC-8 | Implementing a system-use notification system after login of database | Login notifications are not in the MySQL Platform and could not be implemented exactly as the control description. Could be implemented if MySQL was paired with another platform or service.